## Sheet1
Sprint Backlog
Priority | User Story # | Description
1 | 1 | As the System Administrator I want to be able to receive and import Datasets
Analyse sample data for general structure
Establish database relationships
Build database based on strucure and relationships
Translate xls/csv file to JSON data
Add JSON data to database using REST
File select on webpage for data input and import confirmation
Single entry for data input and confirmation
2 | 3 | As the System Administrator I want to have incoming records checked for consistency (i.e. valid date / time values, valid MNC / MCC combinations, valid Event IDs, Cause Codes etc.) and have erroneous records highlighted and excluded
Acknowledge a valid data structure
Parse incoming data into values needed by the table
Check data is consistent with database existing relationships
Invalid data shown to be invalid. Eg. Red font